## historical_calibration
Date | Subject | Notes | Task | Task_status
2022-11-02 | Simple geology model | Running a 3 layer model with top layer conertible only took 30 min (65 mxiter). Doesn't look like 3 layer method has issues with wetting/drying cells. Running calibration of just Ss, Kx hit an issue with parameter change.
2022-11-02 | Model check up | Resetting GHB didn't reduce solve iterations for steady state or following periods. I hadn't rewritten the LPF since I adjusted the TPROGs read in so there was likely a conflict between the LPF HK and the conductances specified in the GHB boundaries and SFR leakage, with this fixed the steady state still hit 200 iter (4 min) but the following periods were more normal (7 iter, 0.03 min), total run time back to 1 hr from 2 hrs. The listing file shows there are several cells in the convertible layer that flip back and forth from dry to wet causing non-convergence (WET( 4,193) WET( 6,194) WET( 9,195) WET( 10,196) WET( 11,197) WET( 15,200) WET( 24,206) WET( 28,210) ), the problematic cells are toward the north east close the edge. During this run I accidentally had vka = hk... Fixing that made run time 54 min (15 faster) | The problem cells don't seem connected to pumping directly, they are half in the low conductivity unit and half out. The cells that continue to be problems after SS are just on the edge of the low K unit, in the pumping cells.
2022-11-01 | Model check up | After updating how TPROGs is read in (flipped), I adjusted the streambed K to sample from strtop to strbot instead of just below model top. I also tested out removing the steady state period in the model to improve starting heads but this caused water budget issues. I also updated the GHB to set heads to 15 ft below land surface rather than at land surface. After making these changes the run time increased to 2 hours with the PCGN solver. | Check cause of increased runtime. 1. Reset GHB fix from 15 ft to 0 ft, 2. Reset SFR calculation of strhc1, 3. Reset CHD inflow elevation, 4. remove convertible layer
2022-06-13 | Calibration set up | In June I got the historical model to run in about 26 minutes with layer 1 unconfined using PCGN. The SS took 60 iterations

## setback_distance
Date | Subject | Notes | Task | Task_status
2023-01-04 | Journal | Call for Papers for “Advancing flood characterization, modeling, and communication” Submission Open: 3 January 2022, Submission Deadline: 28 February 2023 Journal of Hydrology Research-practice nexus
2023-01-04 | Writing | Updated figures to use large and long (type 2), middle ground peak flow and added a summary table providing the total recharge and streamflow depletion. Removed graphic of velocity and made text more anecdotal on reduction.
2022-12-24 | Recharge | Updated elevation data to use minimum elevation from cumulative DEM to ensure consistency in comparison with depth evaluation. This improved flood mapping to show an appropriately small amount during initial flow and substantial inundation at lower elevations at high flow. Updated code to only apply dry cell reduction with an if statement, which ensured no negative flows.
2022-12-21 | Inundation | As part of an effort to improve the flood connectivity mapping, I created subsegments to have more continuous values for the cross-section minimums so that the flood depth isn't under and overestimated by using the midpoint. However after the update there is much more inundation at the upper reaches and much less inundation at lower reaches likely because of a change in the xs minimum from the previous segment value. | I need to check to see how big of a change occurred between segment and subsegment XS min because they should be within a few meters as the slope is generally not too steep.
2022-12-05 | Recharge | Spyder is failing to load the geopandas package which means I can't use it to run the multiprocess. Also the sublime text version isn't able to run properly without any clear error, unless it is taking an exceedingly long time. Found the error in the code that was breaking sublime text (issues with variable referencing and nan), doesn't always show up when in a function. Total run took 2.5 hours for Flood type 2 from Whipple
2022-12-05 | Notebook | While trying to open the jupyter notebook, it kept crashing in chrome because the file size had grown to 100 MB because of the text from error messages. I updated the wetted perimiter method to never be zero and fixed the diff method for identifying inundated cells. Updating the endpoint resulted in much more inundation, probably best substitute since its a simplified method. | Run across all 100 realizations
2022-11-15 | Recharge | Recharge losses look very small when plotted over a large scale of flows. There is still a disconnect in floodplain inundation that should be addressed; one fix could be to create an average XS for the 2000m segment rather than one segment at the end. This would provide more elevation consistency leading to more inundation consistency. Realistically using the bottom segment is problematic because that has the lowest thalweg elevation so it should be corrected by taking the flood depth and adding it to the minimum of each cell within the same segment block
2022-11-10 | Distance | Connec3d 6 pt connectivity should very similar results to the permeameter tests with just slightly higher magntidue as a total of 20% were coarse (after filtering vertical connection) versus only 5% in the permeameter.
2022-10-26 | Connectivity | Set up connectivity analysis for regional tprogs model, recompiled Connec3D to run on my PC and increase max NX, NY, NZ. Required troubleshooting of how to reshape arrays into lines to properly use connec3d. | Compare 6 pt connectivity output with that from the permeameter test by comparing the location/number of cells and recharge results. | 0
2022-10-13 | Connectivity | Met with Alisha, saw there was a significant change in the number of connected components and their volumes between 6 and 18 point which would make it worthwhile verifying 6 pt results. She shared example input/output from her connectivity results
2022-10-07 | Transient | Running a muskingum run creates much too large of flood depths even after adjusting for unit conversion. Running a daily step with adjustment for time the flood is actually on each reach shows a very disconnected flood depth map at the baseline flow of 23 m3/s which is bad because that would indicate trapped flow and at minimum the central channels hould remain inundated
2022-09-27 | Meet with Graham | He thought that I should review whether there are big differences between 6 and 26 point connectivity. He said I should look into the literature to see if any one has already shown flow relates directly to connectivity. He also agreed that it should be the flow vector magnitude not just vertical flow. He directed me to Knudby research papers. | Knudby articles show a variety of connectivity functions aimed at correlating with steady state flow output given a heterogeneous 2D array. | 1
2022-09-22 | Connectivity | When plotting vertical high flow by facies, there was primarily sandy mud and mud with actually a few limited spots with sand/gravel, when looking at qz only. Plotting with the squared sum of qx,qy,qz shows dominantly flow in sand/gravel but not many connected pathways vertically.
2022-09-22 | Connectivity | In the end the connectivity analysis might not be necessary, what if we only looked at the net recharge and included all facies. In the end flood waters will enter all of the facies types and will infiltrate at roughly their vertical conductivity values minus some loss to evapotranspiration for slower regions like muds/sandy muds. The original purpose of the connectivity was to say that these cells would certaintly result in deep recharge on a faster time scale, but if we look at everything then we can assume perhaps a lag. And we could assume this rate will be controlled by near surface saturation conditions because we have a thick unsaturated zone. I think the problem with this is the goal of the paper was suggesting that an understanding of the deeper subsurface is necessary so this would be bascially just saying SAGBI but with geology for soil conductivity which isn't necessarily true anyway
2022-09-22 | Connectivity | I need to meet with Graham to make sure we are on the same page for using the permeameters to identify recharge pathways. I think it is still a good alternative to setting up a full parflow style model becaues it shows spots where the mots recharge would pass through under saturation, the main difference is that under parflow the fine pores will fill before the coarse but then flow will preferentially flow in the coarse once saturated. And again it will drain out of the coarse first leaving more in the fines.
2022-09-08 | Recharge | After talking with Helen, she was interested in using the flood typology paper by Alison Whipple to look at variable types of events rather than certain return periods (e.g., a large winter flood event with a mean peak flow and duration lets us a make a synthetic hydrograph).
2022-08-04 | Setback Recharge | The soil conductivity required a vertical anisotropy to avoid the channel being dried out under flood conditions. Also the recharge results are showing more recharge under the 0 m setback and decreasing benefits with wider setbacks…, was an issue with setback referencing. Use NaN instead of masked array to avoid issue with ID'ing setback numbers. Now I can plot discharge as it decreases due to recharge losses and against each setback variation. | Find a way to plot these discharges and recharge losses across all TPROGs realizations. It is useful to see discharge for one realization, but the value is in the recharge losses. The goal is to identify which setback is providing the most gains (cumulative recharge) so simplify to cumulative recharge across XS and plot setbacks on X axis with recharge on y axis | 1
2022-07-25 | Model iteration | Flow routing informs flood depth and inundated area which is used to identify the area for GW recharge (high flow cells only) then this recharge is subtracted from the flow routing for the downstream reach. | Set up flow routing where upstream recharge reduces downstream flow if significant -> the recharge is a small but somewhat significant portion for wider setbacks (~3% of discharge) | 1
2022-07-22 | Setback Recharge | Look at impact of levee setback on the loss of flushing flow - change in shear force on channel will reduce erosion. What is the minimum scour/flow event we want for a functional flows regime. A reduction in shear force is good in areas with excessive scour but negative where channel alteration is positive according to Helen, this is true to a point for removing debris but the force for debris removal is different than scour depending on sediment type. Helen mentioned clay/silt can't handle velocity above 1.2 m/s before scouring and suggested loooking at Whipple's storm typology paper to look at hydrograph storm response for short vs long events. Compare difference in hydrographs (short vs long) with example unit hydrographs Estimate total losses under varying flood types looking at reach losses and cumulative losses. |  | 1
2022-07-22 | Recharge | The high flow cell maps are what identify critical subsurface pathways and the flood maps identify which ones are activated. I don't need to run recharge scenarios if I overlay these datasets. Then I can fairly say that a 1D darcy equation at the surface would arrive at the aquifer because it is entering in a connected pathway according to a permeamter test. | Overlay high flow cell map with flood inundation map for final recharge estimates. | 1
2022-07-21 | Goals | Optimal setback distance for groundwater recharge (focus is getting water in the ground, not really where it goes from there). Need to know: 1. Flood area and depth 2. Subsurface geology To accurately depict how much recharge arrives at the saturated aquifer or else it is not too different from near surface soil recharge esimates | Consider very simple flood based recharge model runs. Flood should be represented by RIV package with the given depths from the flood depth analysis. Under steady state conditions how much water enters which would again be a simple Darcy's equation. | 1

## Stream_seepage
Date | Subject | Notes | Task
flopy seems to have issue printing out uzf properly as it prints space before nuzf
| Model refinement | When plotting days with flow I realized there was discontinuity at the end of the lake where the streamflow segment taking the return flow had a lower stage than the lake minimum so it was always taking flow even in the summer when it should be dry. Run time 28 min (0.07% CME) Reading the NWT documentation I found that several updates were made to existing packages to ensure sinks don't draw water from dry cells that are considered active but actually don't have water (WEL package cells will be deactivated if in a dry cell). BUT the EVT package was not updated so it will continue to draw water from dry cells which causes budget errors, ideally I should update to the UZF package which will apropriately function by not taking water when a cell is dry.
2023-02-28 | Figures | Finally set up a way to aggregate by segment or date then save that output to save time setting up figures Plotting a time series of seepage grouped by facies is really hard to distinguish individual lines, but that works when aggregating across
2023-02-27 | Model refinement | When the model hits later summer streamflow goes to near zero and if we assume no other forms of recharge then there is only storage to draw from, and it seems that that causes the most issues in percent discrepancy. I wonder if the regional groundwater elevations are lower than they should be? Fixing this issue in the GHB package with heads below cell bottoms (setting them to the midpoint elevation of the cell) and using 5000 m seems to have fixed convergence issues (maximum timestep/period error is now 0.16 percent), only takes 16 min. One stress period in late 2016 has 1% error but that is small error and a very short period likely due to rewetting (0.2 NSE) Using 500 m distance gives run time of 29 min, but 12 steps with mxiter and 0.27% error, and peak model errors of 3% during dry periods. (0.4 NSE) Using 1000 m distance gives 27 min, 6 steps with mxiter, 0.10% cme, peak model errors of 1.5% (0.34 NSE), slight adjustment to ghb elev (add half thickness) decreased max error to 1% NSE from 0.34 to 0.33 | I'm going to settle with the 1000 m distance as it balances model convergence (1% max error) with matching realizations (NSE = 0.33) and run time is about 1/4 of previous
2023-02-27 | Model refinement | Found consistent error above 5% for 4 year run in 2014 and 2015 dry season when too much pumping causes conflict with GHB likely. Went through and further id'd land that would be fallow based on field experience with satellite (where riparian/drainages) Updating pumping reduced it by 15% but the error remained ( too much outflow) GHB outflow increased to compensate. It seems like GHB is too controlling on the system or perhaps SFR steady state flow needs more tweaking? I re-ran the entire Jupyter Notebook for oneto_denier_2014_2018 after updating it to 1 step per period and found starting at the steady state error was only 1%, there might have been an error introduced with conflicting conductivity values in packages. Maybe when setting up re_connection run? (cbc file was smaller 1.6 instead of 9GB) Model does run quicker with less steps, 31 min total, but checking zone budget shows error of 7-8% during fall 2015, 2016 Tried setting GHB distance to 1000m from 500 but still had around 5% error in dry periods | Also in aggregation, I am not using subdaily data so I might as well aggregate to 1 timestep per period to see the effect. 100 runs took 6.5 hours
2023-02-27 | Post-processing | Be careful when post-processing data stream data by reach, column because grid_sfr will have two cells with multiplle segments where they are used for connecting the floodplain. Instead join by segment, reach
2023-02-27 | Parallel | Takes 32.6 hours to run 100 realizations in parallel Potential issue with sfr strhc1 is that dividing sand and gravel by 10 to assume clogging makes them essentially HK of sandy mud so we have 34.5, 12.9, 21 the 0.56 VKA for gravel to mud. But realisticially it is the geology below that makes the bigger impact so this may not matter. But this means that we should not group by strhc1 but the geology of the cell below
2023-02-23 | Parallel | Updated code to write out the parallel input files, biggest updates to GHB with new set up. Realization ran fine 2 hr 30 min with error in reasonable range, less than 1%. Used sublime text to run parallel realizations
2023-02-22 | GHB | The multi year run may also have been using a 5,000 m distance for the GHB which may signifcantly impact steady state by allowing more water in or out. Run time took 2 hr and 16 min (CME = 0.89%) The NSE went from 0.39 to 0.46, R2 from .13 to .38 , and hydrograph fit did look slightly better. 82/8676 steps hit mxiter (500)
2023-02-22 | Multi year | Setting up new steady state: The median for 2018 is 1.25 times larger than the median for WY2015-2018. The meidan for WY2011-2014 is only 0.93 times smaller than WY2015-2018 so not to significant The rainfall from WY2011-2014 is 1/40 the rainfal from WY2015-2018 Updated RCH, EVT, WEL, LAK package with new ET and rainfall. Set steady state GHB to just use heads in fall 2014 for steady state as well. Playing around with SFR package steady state flow, I reduced the median flow by 3/8 to get heads in the monitoring wells that are on average where they should be. I also added back the sand/gravel 1/10 reduction in sfr and lake for clogging. 1 hr 49 min, 0.12% error
2023-02-21 | Multi year | The seasonal dynamics look good on all wells but variable in terms of match. MW 22,19,23, 13 are relatively tight. Initially MW 9,2,20,5,3,17,CP1 are offset then are closer to the observed. MW11,OA,7,14 are consistently offset. For the initial offset it is likely an issue with the amount of recharge and stream leakage in the steady state run being over weighted by 2017 wet year when the historical system is predominantly dry. | Ideally I should set steady state conditions on the previous years hydrology with some influence from previous years
2023-02-21 | Multi year | Added recharge term and reduced run time to 28 min, homogeneous version only took 17 min (0.01% error in both) Increasing ET extinction depth to 10m for all cells helped ensure heads declined sufficiently in the summer (41 min with 0.01%). Steady state still a little high so may need to up the ET rate under steady state or decrease recharge which is typically because assuming average recharge in steady state is going to over-estimate as more would runoff and antecedent conditions tend to be drier. Maybe running multiple years would improve this as the impact of steady state would decrease | Run multiple years to look at how seepage changes with time and the role of heterogeneity in wet vs dry years.
2023-02-20 | GHB | Review model budget with updating buffer distance and low distance GHB. Consider monthly changing GHB, with averaged SS. Took 55 min | Percent discrepancy maxed at 1% in later timesteps, most likely issues with drying
2023-02-20 | Grid | Complexities arise when dealing with 100 vs 200 for SFR cross-section spacing. It would be faster in terms of programming to keep with 100m and add maybe a 2,000m buffer instead of 4k to avoid higher computation cost. Model took 53 minutes
2023-02-20 | Grid | Small oneto-denier model with 1,000 m buffer from monitoring well boundary box and 100 m cells had 55 by 63 cells. Jumping to 200 m cells had 17 by 21 cells. And adding a 5,000m buffer increased dimensions to 57 by 61 cells. At the size the 2m DEM is insufficient at the upstream end (stops before HWY99) so I will need to either join the XS data with the HEC-RAS dem XS or switch to the 10m DEM. | Run model with stream starting short of up stream model boundary or reduce from 5,000 to 4,000 meter buffer at which the xs_all reaches the upper end of the grid
2023-02-19 | Water Budget | Changed SFR numtim (number of substeps) from 5 to 1. Took 1 hr 7 min, CME was 0.2%. Now the error in the cbc file lines up with the list file, might have been an issue with numtim in SFR causing a split output or something, also the time step might have been so small it caused issues with sfr calculations I think the long run time was mostly due to the tighter convergence criteria 15 instead of 500 and 1000 iter instead of 500 -> back to 31 minutes
2023-02-16 | GHB | At some point whne updating the GHB package I updated the distance from 5000m to 500m to represent the fact that the heads are at the model boundary, this allowed for much more groundwater outflow than before, no longer hardly any surface water return flows. Now it might be worth considering expanding the domain to reduce the outflow rate. Realization 000 ran in 9 min and it had the original distance of 5000 m. With lower conductivity we see more pumping, more outflow to the lake and much less flow to the GHB. Doesn't seem to be a big change in head contours or hydrographs | Consider different GHB distance or expand model boundary Percent discrepancy in zone budget was all below 0.3% (largest peak) on a daily scale when GHB was 5000m
2023-02-18 | Water Budget | It seems like there is a very slight difference between the flopy zone budget and the modflow OWHM budget because the OHWM budget doesn't show error above 5% Example case: Stress period 3. For timestep 6 Stream leakage out is recorded as 54 in list file but 104 in flopy zonebudget, and for stream leakage in the discrepancy is about 500 Is there any chance the sfr set up is causing issues like having sub timesteps? | Should try running with NWT instead to see if OWHM has a code issue. Although I'm assuming the list file is correct and flopy is at fault. Should also check by running zonebudget tool
2023-02-18 | SFR | After adding segments to have proper flow routing the run time was 50 min, CME = 0.42%, 55 min when printing output every timestep. It's odd that even just the first few periods have around 20-40 iterations when it previously was 6-7. Even spd 3, ts 1-3 have error of 24% because of too much water leaving the system (storage, stream leakage out), convergence criteria are met Although it took much longer, fixing the routing so water continued downstream avoided the under prediction that was happening in a lot of wells.
2023-02-16 | SFR | Reviewed MODFLOW source code and identified that MODFLOW SFR only sums tributary inflows. Everything else such as lake inflow or a diversion is set as Qin and overrides other values. | Need to add a segment between the floodplain diversion segment and the downstream segment. And need to add a segment at the floodplain outflow to avoid deleting downstream inflow
2023-02-14 | SFR | Finally did a plot of the streamflow profile and realized that no flow occurs after segment 21 which is the diversion to the lake. And flow only occurs at the far downstream end due to return flow, need to double check diversion criteria. It is not clear why the diversion from upstream doesn't follow outseg. Removing the iprior of -2 with 0.5 made it so the flow was as it should be in the stream channel, until the lower segment where flow returns to the channel then flow zeroed out. The flow into segment for floodplain diversion is also always near 0 even when it should be diverting, but the flow profile shows an expected drop in flow during peak flow events I think the flow in is failing when there is also an iupseg diversion into a segment, I may need to start from scratch without the diversions and then add them one at a time to see what works. It might be that having the flow to the lake and upstream diversion at the same time is too much An alternative set up would be to have all flow go to the diversion segment then divert all that flow and allow 50% to return above the cutoff
2023-02-14 | Model setup | Running model with added GHB boundary had 21 min runtime, 0.15% CME.
2023-02-14 | GHB | Finished updated method for creating GHB given row,cols and head values. Rather than dealing with LGR which can be quite difficult Steffen suggested I just upscale the entire grid as so. For the lower Cosumnes I could just expand the model grid to avoid boundary effects, and there isn't a huge reason to use 100m instead of 200m grid size cells since I don't have any fine scale in-stream measurements.
2023-02-10 | Modpath | Initial forward tracking shows essentially all termination in zones ('weak sinks') and the map of the end points suggests very close points to the stream network from a top view. - After updating to pass_through weak sinks the particles all almost immediately (0 to 1E-7 days) stop and are stranded - Even releasing particles everywhere in the domain we see them all terminate immediately (stranded) - Updating OC so every period and step has a cbc and hd file made it so the particles had an age of 0.83 days? Or 0.83(4 hours)?, everything still has a status of stranded (that was with setting particles 1 layer deeper than the sfr layer). 0.833 corresponds to the first release time - Particle tracking runs slowly at first then quickly passes through later stress periods even with deeper sfr layer - I may need to specify aux for the budget and relevant packages (SFR, GHB, WEL), this was already set up I think in the compact budget. - The real error was that iphdry the variable that specifies whether hdry (-999.99 or -1E30 should replace the value of dry cells), normally this is 0 for packages like HOB which will assume the hdry value is a real value - The problem in the end was the OC package only had the cbc written once per stress period so particles were being stopped immediately when modpath found the cbc for the next timestep didn't exists. With OC adjusted to print cbc/hds for every step the modpath run takes the full time (and all particles remained active)
2023-02-07 | Boundary Conditions | The model is showing a larger than realistic pumping depression below the field site which means either too much pumping or not enough inflow from the delta
2023-02-07 | Homogeneous | The hydrographs between the homogeneous and one heterogeneous are not so different. The groundwater contours showed the most noticeable difference, in the homogeneous case they were much more uniform and no pumping depression formed on the eastern boundary. Checking the packages showed the SFR/LAK package hadn't been written with uniform VKA properly, instead variable from tprogs
2023-02-07 | Error | Comparing the R2, RMSE, NSE from the parallel set up with flow error of 500 m3/d and maxouter of 500 to the test model with 15 m3/d and 500 maxouter showed slightly worse values so tighter convergence criteria help with matching reality as well (probably avoids extreme stage values). When considering model error 500 m3/day is 1/5 of a cfs so 500 is really sufficient.
2023-02-07 | Homogeneous | Running with udpated work from complex model only takes 10 min (0.1% error)
2023-02-07 | Model fit | Playing around with the model set up to improve water budget error reduced the NSE and increased RMSE slightly. Not sure if this is because of the reduced sfr/lake vka or just because of reducing the number of cells. I noticed Oneto-Ag wasn't included in hobout because of naming convention issues. The issue with not enough dry season drawdown again is odd because I'm not sure what could have impacted it. The solution would be to reduce the number of unconfined layers to cause more head fluctuation with storage change or to increase horizontal conductivity to increase drainage rates. What's tricky is that some of the worst performing realizations have too much drawdown so it's not something I should really play with. I could adjust it to match for the steady state and then leave as is?
2023-02-06 | Parallel | I re ran the parallel runs but I didn't include the upate for maxiter from 500 to 100 or fluxtol from 500 to 15. But those didn't make a big difference anyway
2023-02-06 | Lake | The lake bathymetry set up I had been using was converting the units from ft to meters when it was already in meters so lake volume was essenentialy 1/10 what it should be per stage. Didn't make a noticeable difference. It actually did make a difference I had coded the lakarr correction wrong where I only used cells over the stream, fixed that so now there are no cells over streams and error CME was 0.12%. Runtime 16 min
2023-02-06 | Error | Setting NWT flow tolerance from 500 to 15 didn't improve. Need to reassess if there is a descrepancy in the set up of the lake package. I removed LAK grid cells that had less than 50% coverage of a cell also because there is likely some overlap with SFR grid cells. Max error started at 16% then quickly went to near 0 within several stress periods. Cumulative volumetric error is 3.84%
2023-02-06 | Error | Cumulative error is still hitting 11% after adjustments because in spd 50 the error hits 38% and doesn't return to near 0 after that. I need to assess if the lake is the cause of these issues by removing it. It might also take tighter convergence criteria because the model is solving each stress period quick so it isn't being required to converge sufficiently. Without the lake package the model hits an error of 16% at spd 50 then returns to near 0% error within 2 stress periods. For the Blodgett Dam project I used a theta value of -0.75. The error propagation was the same with 0.75 I used 0.5 for the lake water budget for the setback_streamflow run, this had the same results as before. There must be a need for convergence criteria then.
2023-02-02 | Homogeneous | I set up a homogeneous model run that averages all values to one for hk, vka. HK is sandy mud, vka is mud. Issue is that the cumulative mass error was still 9% so it may be that the clogging layers are not the issue?
2023-02-02 | Error | Finally realized that the mass budget error is very large during the peak flow event leading to an unacceptable cumulative mass error. Increasing the maxouter from 500 to 1000 didn't make a difference beside runtime. I'm going to scale back lake bed and sfr vka by 1/10 again as realistically they should be clogged at least in the sand and gravel. The error actually increased to 14%
2023-02-01 | SFR | Adding the unconfined, OWHM through an error finally saying the streambed bottom elevations were below cell bottoms, maybe in confined conditions it asssumes this is a non-issue. I found the issue and corrected the SFR layer but OWHM kept raising an error until I added the option FIX_STREAM_BOTTOM (30 min) The monitoring well dynamics look pretty good after adjusting the top 5 layers as unconfined, now pumping doesn't draw them down too much and we still see proper rise. The only other adjustment would be to set a higher threshold for floodplain inundation because some wells seem to have to much recharge in smaller, earlier events
2023-01-29 | WEL | Adding pumping for the agricultural production in the area caused a drawdown of 15 m in the following season which is 10 m + more than needed. After removing pumping where there are GDE's identified (a reduction of 1/3-1/2 for the SS), the dry season decline was only 5 m too much, it might also be that I'm still simulating a confined system when this should be a semi-confined system. The pumping for the summer should be 0.6-1m of water which for Sy of 0.25 is 2.4-4m decline but 0.1 would be 6-10m. In confined terms we have Ss*b of 0.001 to 0.004 which would be even more. Let's run a test of the system unconfined (previous run times were 9m on avg)
2023-01-29 | DIS | Deepened model thickness from 20m to 40m to allow inclusion of agricultural pumping in deeper layers to draw down head during the summer and also improve characterization of Oneto-Ag which is screened deeper (avoids boundary effects on other wells too). Adding the extra layers seems to have buffered the effects of groundwater change due to stream flow - > messed up lake package.
2023-01-27 | Lake | Added average evapotranspiration rate to lake because I believe ET is removed with no flow cells. The issue might be that if the lake stage starts below the minimum then modflow can't bring it back to saturation even with inflow. I updated the THETA NSSITR SSCNR SURF parameters to use shasta's -1 > 1, 0 > 1000, 0.01 > 1E-5 and 0 > 0.02 (1 1000 1E-5 0.02) which then made the lake have stage changes. Now the lake stage gets way to high because there is a lot of inflow and the only outflow is seepage and ET, need to add the surface water outflow. (Runtime jumped to 27 minutes) Adding lake outflow brought runtime back to 7 min.
2023-01-27 | Lake | The water levels are undersimulated in the lake which is because right now the lake is only acting as an outflow of groundwater, it isn't causing recharge. Need to see if there isn't flow entering the lake. Or if lake minimum is too low?
2023-01-26 | Runtime | After fixing the DEM issue in the SFR package, runtime reduced to 8 min. And now simulated peaks are upt to 7 m but the baseline gwl levels are higher as expected because the stream level is higher. This could mean that ET could be higher or maybe deeper?
2023-01-26 | SFR-DEM | It is important to note an update in shapely caused a change in code. The NHD line string must be inserted into linemerge() after applying a unary_union. And the linemerge function is critical as it joins the line strings based on the closest end points which is key to properly sorting the line into a good direction.
2023-01-25 | DEM | The monitoring well ground elevations sampled from the 2m DEM (from Lily Tomkovic) are within ~0.5m of the elevations found with the regional 10m DEM so it is unlikely a data issue at the well heads for the observation data. There is a 2-8m discrepancy between the regional 10m and local 2m DEM when we look at the stream top. And this impacts how much seepage we have from the stream to the adjacent cells. The cause was when writing out the XS data, I had forgot to adjust for the conversion or lack thereof from ft to meters that was put in previously for the HEC-RAS dem. Stream top now shows expected range of 5-2m rather than 2-0.5.
2023-01-23 | SFR | tried removing reduction of 1/10 to sfr vka to see if that increases signal in GW response
2023-01-23 | Lake | I'm curious why the lak package requires basic package to be negative, this messes with MW23 which is screened in layer 1. I updated the screened depth for MW23, Oneto-Ag and now they are below layer 1 so no issue
2023-01-23 | Lake | 11 min run time after making SS for lake dry
2023-01-23 | Lake | after adding the lake to the simulation, the run time is still only 14 min long, although issue in SS with high GWE due to lake steady state,
2023-01-23 | Runtime | Fixed SFR layer, removed EVT where there were SFR cells. run time was 17 min after removing EVT under sfr cells and fixing sfr layer
2023-01-18 | SFR layer | changing the sfr layer really impacted the VKA for SFR because I had defaulted the layer to 0, but changing the dem meant the str top was lower than it was so there was likely a conflict between the UPW VKA and SFR VKA.
2023-01-18 | Channel elevation | original Oneto-Denier dem, max sim GWL around 3-4 m. raising the str top by 4 m brought max sim gwl to 6-8 m and the sim values were raised so the mean level was higher to the peaks seen in the obs, but is to far above the dry season lows. There isn't a large peak still so the peak is likely due to over bank flooding
2023-01-18 | Channel elevation | adding 4m to the str top had run time of 48 min
2023-01-18 | XS delination | the smaller peak flows might also be a result of the cross-section change resulting in different depths/widths or even different stream bottom elevations
2023-01-18 | Packages | adding the missing sfr segments brought up the steady state levels so that even with ET the model matches with observed, now the peaks of gwl are well above the simulation which is likely because we aren't simulating the flooding or precipitation from winter events
2023-01-18 | SFR | Adding the extra stream segments could have increased conflict with EVT? run time was 37 min
2023-01-18 | SFR | The HEC-RAS dem only extended to the upper end of Oneto-Denier, so the original model runs which ran in 3min actually only had SFR for the first 1/3-1/2 of the domain. I ran the XS code again for the 1m dem from Alison Whipple but now the code runs slow and has issues. It doesn't seem like it's the VKA because the first few segments have the highest conductivity.
2023-01-18 | Initial set up | With the outflow the head within the basin is largely controlled by the GHB head (ranges 5-15m, gw head below river defaults to 10m) which is not desirable. I need better justification for the outflow choices. Parsimony dicatates less is more.

## Levee_removal
Date | Subject | Notes | Task
2023-02-24 | Parallel | Update or copy the parallel code to write the 10 best realizations but without the floodplain connection.
2023-02-24 | Realizations | Using the historical model for Oneto-Denier I can select the 10 realizations with the best matching NSE/RMSE to simulated Oneto-Denier if levee setback had not occurred.

## model_development
Date | Subject | Notes | Task | Task_status
2023-02-22 | UZF | I should update the pre-processed evapotranspiration and precipitation data to be saved in a binary format with h5py to speed up loading when building models later. Loading the text files for each year takes a long time | Updated so everything uses hdf5 | 1

## economic_model
Date | Subject | Notes | Task | Task_status
2022-11-16 | Crop Model | LandIQ lumps pasture together with Alfalfa which is problematic as the crop water model is very different between these two. Goal of having something workable by second week of December. | Plot the LandIQ over the USDA CDL data to determine where there is a difference between pasture and alfalfa (pick by majority in parcel). We also need to distinguish between irrigated and non-irrigated.
2022-11-16 | Coupling | Cameron would like to get the output from Stata to a clean format for the physical model. The Stata model will output coefficients that needed to be ordered in an array and then applied as the coefficients for the multinomial regression. There is a correlation between the groundwater level and the crop choice observed in each parcel that calculates the correlation coefficient, then in future years when modflow returns a groundwater level the crop is estimated based on the coefficient and groundwater level. 5 crop profit models: Field crops, pasture, grain and hay, vineyards, other, and fallow. The water/profit function is a better way to parse out how much water comes from groundwater vs surface water than assuming all ET comes from groundwater. | Can we reach out to OHWD about where there are diversions in the Cosumnes River. The GSP didn't have any clear information about diversion points. This may not matter if outcomes are not sensitive to surface water. Is there an overlap of acres of pasture vs alfalfa? It's generally not advised to use alfalfa and pasture in the same plot
2022-08-19 | Coupling | The economic model is almost done and is ready to be coupled or at least tested with the regional model. There was some question about differentiating between groundwater and surface water constraints used in the model, I explained that at a monthly check-in pre-processing should be sufficient. How do we find out which parcels have surface water vs groundwater.
2022-07-25 | Regression | Multinomial logit regression needs slope and soil quality. Determine slope in degrees and percent using 10 m DEM and upscale to model grid and parcel scale. Return zonal statistics for each parcel (mean, max, min, std dev, median) Info on parcel access to surface water (water rights data is convoluted) -> conveyance structure data? (ditches/canals) -> does CEQA permits identify near stream construction?? -> irrigatoin district maps/data (Galt Irrig. Dist, OHWD) Multi-nomial and mixed logit regressions are better for projecting economics than original version of economic regression | Calculate slopes statistics for parcels and model grid | 0
2022-07-13 | Model coupling | The crop model will need to provide monthly inputs into the hydrologic model and vice versa (it is necessary to see the effects of crop choices month by month on groundwater conditions) To accomplish this the hydrologic model will be run month by month while the economic model runs between and then provides updated crops/irrigation that create new model inputs for the MODFLOW model which uses groundwater levels from the previous MODFLOW model as starting heads. Example \model_dir (includes SFR/UPW/GHB/CHD = do not change) \jan_20 \feb_20 \mar_20 .wel, .bas6, .uzf/.rch (dependent on ag decision/ previous heads) 1. Write out base directory with static files 2. WRite out monthly directories 3. Write script to load previous head output and rewrite start heads 4. Be ready to change existing RCH/WEL script for varying ET/recharge input | Test new model directory with monthly start/stop of model | 0
2022-07-13 | Yield | Yield-irrigation curves are season cumulative -> we need to translate to impact from each cutting ->over irrigation has a capped yield but no damage Daily or monthly time step depends on when irrigation and cutting decision occurs. Although cutting is typically not aligned with the 1st of the month the decision is on a monthly scale. Irrigation can be more easily tied to the 1st of the month | None | 0
2022-07-13 | Crops | Are low acreage crops needed? E.g., nursery, fruit, nuts? There is no yield-irrigation information | None | 0
2022-07-13 | Crop model | Unit of analysis: county tax assessor parcels (current is 2022 parcels). Crop type change between eyars for CDL versus LandIQ data, is the change capture by CDL significant? | Compare USDA NASS CDL maps to LandIQ | 1
2022-07-13 | Regression | Multinomial logit regression: given elevation, slope, aspect, soil type, groudnwater levels, water year forecast, past years crop, what is the likelihood of a given crop | None | 0
2022-07-13 | Water | EWRIMS -> gives distance to surface water right for each parcel (helps define riparian as yes or no) Is pump drawdown an impact that is necessary to represent in the model when considering the regression? The model is averaged pumping so perhaps unnecessary as we can't reach that level of refinement, and drawdown from pumping would most likely somewhat uniformly impact all wells (similar hydraulics) | None | 1

## temperature
Date | Subject | Notes | Task | Task_status
2022-07-22 | Alternate models | Temperature mixing model to add additional component for gw inflow term in addition to semi-empirical model? This would causes a double accounting although. Better option is to use heat budget model from ECI240 on Water Quality Modeling. Look at travel time from Michigan Bar and downstream point to determine the expected linear change downstream and with time from some upstream point (assuming gain is from solar radiation only)

## Advice notes
Person | Advice
Yusuke | Uses slides for working group meetings before transitioning to writing a draft in a word document
gdal is downgraded when isntalling rasterio after geopandas in python 3.11 with conda